## Overall
OCR Invoice Automation PoC: build and 5-year run
All costs in USD. Cloud: Azure retail list prices in southeastasia fetched 2026-09-28, no discounts or reservations. Blue cells are inputs; black cells are formulas; green cells link to other sheets.
Inputs
Input | Value
Days of delivery (working days) | 32
Working days per month | 21
Months of delivery
Hours per month (always-on services) | 730
Delivery start date (optional; dates the epics and sprints)
Working days per sprint | 10
Years of run after go-live (3 to 5) | 5
Yearly increase in run costs | 0%
Run years, with the yearly increase
Contingency | 0%
Exchange rate (1 USD = x USD) | 1
Delivery team (build)
Role | Day rate (USD) | Employees | Days on delivery | Allocation | Mandays | Cost (USD) | Cited from
Team member (blended) |  | 2 |  | 100% |  |  | assumption: 2 people for 32 days (30 stories at ~1 story/day, AI-assisted, plus 2 days slack); Dj to confirm
Total
Run support (OPEX): IT support and maintenance after go-live
Role | Day rate (USD) | Mandays per year | Cost per year (USD) | Cited from
Team member (blended) |  | 12 |  | assumption: 1 day a month for patching, dependency upgrades, DB start/stop and alert triage; Dj to confirm
Total
Cost summary
Item | Monthly (USD) | Months in delivery | Delivery cost (USD) | Run months per year | Run cost per year (USD) | Run cost over the horizon (USD) | Total (USD) | From
Shared environment |  |  |  | 12 |  |  |  | Shared sheet
Dev environment |  |  |  | 12 |  |  |  | Dev sheet
Prod environment |  |  |  | 12 |  |  |  | Prod sheet
Delivery team | [7 empty] | Delivery team table above
Run support (OPEX) | [7 empty] | Run support table above
Recurring run costs | [7 empty] | Run Costs sheet
Other one-off costs | [7 empty] | Other Costs sheet
Subtotal
Contingency
Grand total

## Multi-Year
Multi-year view
In USD. Build is the delivery; each year after go-live carries the run costs, raised by the yearly increase, and the revenue given for it. Years past the horizon (Overall input) show zero. Contingency applies to every cost.
Category | Item | Build | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Revenue |  | 0
Revenue |  | 0
Revenue |  | 0
Cost | Build: delivery team, environments during delivery, one-off costs |  | 0 | 0 | 0 | 0 | 0
Cost | Shared environment (run) | 0
Cost | Dev environment (run) | 0
Cost | Prod environment (run) | 0
Cost | Run support (OPEX) | 0
Cost | Recurring run costs | 0
Contingency | Contingency on every cost
Total revenue
Total costs
Net
Cumulative net
Payback
Return on cost (net / costs)

## Epics
Epics: deliverables, forecast and actual
In USD. Forecast: each epic takes a share of the build in proportion to its planned working days (that share of the delivery team and of the environments during delivery), plus the one-off costs tagged to it and its Claude API budget; dates run the epics one after another from the delivery start date. Actual: enter or keep the actual start and end dates; actual working days, the Claude API actual from the ledger, and team and infra scaled by actual / planned days (same team and rates) unless you enter the timesheet team cost. Blue cells are inputs; add an epic in a spare row.
Epic | Name | Deliverables | Planned days | Planned weeks | Planned start | Planned end | Share of build | Team mandays | Team cost (USD) | Infra cost (USD) | Other costs (USD) | Claude API budget (USD) | Forecast total (USD) | Actual start | Actual end | Actual days | Days variance | Days variance % | Claude API actual (USD) | Actual team cost, timesheets (USD) | Actual total (USD) | Cost variance (USD) | Cited from
1 | Suppliers can upload invoices by link | Stories 1.1-1.9: Terraform, CI/CD, API and web skeletons, monitoring, supplier links, upload, device quality check | 9 | [8 empty] | 54 | [10 empty] | _bmad-output/planning-artifacts/epics.md Epic 1: Suppliers can upload invoices by link
2 | Invoices are read and checked automatically | Stories 2.1-2.11: quality stage, pipeline recovery, DI extraction, PO sim, validation, staff sign-in, admin queue | 11 | [8 empty] | 66 | [10 empty] | _bmad-output/planning-artifacts/epics.md Epic 2: Invoices are read and checked automatically
3 | Clean invoices post to the accounts system | Stories 3.1-3.4: accounts sim, auto-post, admin approve, search | 4 | [8 empty] | 24 | [10 empty] | _bmad-output/planning-artifacts/epics.md Epic 3: Clean invoices post to the accounts system automatically
4 | Deliveries tracked, overdue suppliers reminded | Stories 4.1-4.4: goods-in scan, overdue list, reminders, delivery dates page | 3 | [8 empty] | 30 | [10 empty] | _bmad-output/planning-artifacts/epics.md Epic 4: Deliveries are tracked, and overdue suppliers are reminded
5 | Supplier price and speed insights | Stories 5.1-5.6: analytics refresh, alert emails, price comparison, watchlist, scorecard, finance view | 5 | [8 empty] | 36 | [10 empty] | _bmad-output/planning-artifacts/epics.md Epic 5: Finance and procurement see supplier price and speed insights
Total
Formulas:
Planned end = IF([Planned start]="","",WORKDAY([Planned start],[Planned days]-1))
Actual days = IF(OR([Planned days]="",[Actual start]="",[Actual end]=""),"",NETWORKDAYS([Actual start],[Actual end]))
Planned start = IF(OR([Planned days]="",ProjectStart=""),"",WORKDAY([Planned end, row above],1))

## Sprints
Sprints: forecast and actual
In USD. Every sprint is a timebox of the Overall input 'Working days per sprint' from the delivery start date. Forecast: the sprint's planned working days (the days of delivery, sprint by sprint) at the delivery team's and the environments' daily cost, plus any Claude API budget. Actual, up to the last actual activity (the latest completed story or day of Claude usage): the days worked in the sprint, the stories completed, the Claude API cost on its days, and the team at the days worked unless timesheets are entered. Sprints past the plan appear when work ran over. Blue cells are inputs.
Last actual activity
Sprint | Start | End | Planned days | Planned stories | Team cost (USD) | Infra cost (USD) | Claude API budget (USD) | Forecast total (USD) | Days worked | Stories done | Stories done (list) | Claude API actual (USD) | Actual team cost, timesheets (USD) | Actual total (USD) | Cost variance (USD)
1
2
3
4
5
6
7
Total
Formulas:
Start = IF(OR([Planned days]="",ProjectStart=""),"",WORKDAY(ProjectStart,(1-1)*SprintDays))
End = IF([Start]="","",WORKDAY([Start],SprintDays-1))
Days worked = IF(OR([Start]="",LastActual="",[Start]>N(LastActual)),"",NETWORKDAYS([Start],MIN([End],LastActual)))

## Phase Budgets
Phase budgets: Claude API budget and actual per planning phase
In USD, at Claude API list prices. The budget each planning phase may spend (test design, governance, diagrams, course corrections ...), set once the epics and sprint plan are done; the epics and sprints carry their own budgets on their sheets. Actual: the phase's Claude cost from the ledger (Claude Usage Detail) once the close-out sheets are in. A control figure: not added to any total. Blue cells are inputs; name a phase as the token ledger does.
Phase | Claude API budget (USD) | Claude API actual (USD) | Variance (USD) | Variance % | Cited from
planning changes (correct course) | 10 |  |  |  | owner: Dj, 2026-09-28
test design | 8 |  |  |  | owner: Dj, 2026-09-28
merges, promotions & deploys | 5 |  |  |  | owner: Dj, 2026-09-28
governance (Jules) | 5 |  |  |  | owner: Dj, 2026-09-28
architecture docs (Da Vinci) | 4 |  |  |  | owner: Dj, 2026-09-28
token reporting | 2 |  |  |  | owner: Dj, 2026-09-28
Total

## Revenue
Revenue
Revenue the solution earns, per year after go-live, in USD, from the owner or the business case; each stream cites its source. Years past the horizon are ignored. Blue cells are inputs.
# | Stream | Basis | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Cited from | Note
Total

## Rate Card
Employee rate card
Day rates in USD. Source: Dj, in chat 2026-09-28: blended average day rate; updated 2026-09-28. Blue cells are inputs; the team and support tables look roles up here.
Role | Day rate (USD) | Note
Team member (blended) | 800 | average across roles

## Other Costs
Other one-off costs
Licences, tests, training and other one-off costs of the build, outside the environments and the team, in USD.
# | Item | Amount (USD) | Cited from | Note | Epic
Total

## Run Costs
Recurring run costs (OPEX)
Yearly costs of running the solution outside the cloud environments and the support team: support contracts, licences, subscriptions. In USD per year; the Multi-Year sheet escalates them by the yearly increase.
# | Item | Annual cost (USD) | Cited from | Note
Total

## Shared
Shared environment
Azure retail list prices (pay-as-you-go) in southeastasia, USD, fetched 2026-09-28. Daily cost is the monthly cost spread over the year (x 12 / 365). Blue cells are inputs.
# | Component | Azure service | SKU / tier | Unit | Unit price (USD) | Quantity | Usage per month | Monthly cost (USD) | Daily cost (USD) | Annual cost (USD) | Cited from | Price source | Note | Environment
1 | PostgreSQL Flexible Server compute | Azure Database for PostgreSQL | Burstable B1ms | 1 Hour | 0.026 | 1 | 261 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-12 | Azure Retail Prices API, Azure Database for PostgreSQL Flexible Server Burstable BS Series Compute / B1MS, southeastasia, USD per 1 Hour, meterId caa13868-6d59-5b82-ae7a-765904be9712, fetched 2026-09-28 | AD-12 [ASSUMPTION] up-hours weekdays 09:00-21:00 SGT = ~261 h/month; stopped by hand otherwise | Shared
2 | PostgreSQL storage | Azure Database for PostgreSQL | Flex Server Storage | 1 GB/Month | 0.138 | 32 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-12 | Azure Retail Prices API, Azure Database for PostgreSQL Flex Server Storage / Storage Data Stored, southeastasia, USD per 1 GB/Month, meterId 3dc8bdb7-8a94-5ffe-8836-6e80a540f61f, fetched 2026-09-28 | 32 GB, billed while stopped; 7-day LRS backup within free allowance | Shared
3 | Document Intelligence | Cognitive Services | F0 (free) | 1K pages | 0 | 1 | 0.5 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-8 | Free tier F0: $0 per AD-8; S0 would be $10 per 1,000 pages (not looked up) | 500 pages/month cap shared by Dev and Prod | Shared
4 | ACS Email | Email | Basic, sent email | 1 | 0.00025 | 1 | 250 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-16 | Azure Retail Prices API, Email / Basic Sent Email, southeastasia, USD per 1, meterId 91348e14-8d9f-561e-ba5e-06be5a2c7a89, fetched 2026-09-28 | assumption: ~250 alert emails a month across Dev and Prod | Shared
Shared
Shared
Shared
Total

## Dev
Dev environment
Azure retail list prices (pay-as-you-go) in southeastasia, USD, fetched 2026-09-28. Daily cost is the monthly cost spread over the year (x 12 / 365). Blue cells are inputs.
# | Component | Azure service | SKU / tier | Unit | Unit price (USD) | Quantity | Usage per month | Monthly cost (USD) | Daily cost (USD) | Annual cost (USD) | Cited from | Price source | Note | Environment
1 | Stage queues | Storage | Queues v2 Standard LRS, Class 1 operations | 10K | 0.004 | 1 | 30 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-2 | Azure Retail Prices API, Queues v2 / LRS Class 1 Operations, southeastasia, USD per 10K, meterId a7193db3-642b-4d6f-ad03-ed5f00153bbd, fetched 2026-09-28 | assumption: ~300K ops/month from queue-trigger polling, matching AD-2's ~$0.12/month | Dev
2 | Blobs: images, corrections (30-day) | Storage | Block Blob v2 Hot LRS | 1 GB/Month | 0.02 | 1 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-15 | Azure Retail Prices API, General Block Blob v2 / Hot LRS Data Stored, southeastasia, USD per 1 GB/Month, meterId fc203689-76e7-4fbe-86b9-968d73231c00, fetched 2026-09-28 | assumption: 1 GB held under 30-day lifecycle (DI page cap bounds volume, AD-8) | Dev
3 | Tables: links, keys, reminders | Storage | Tables Standard LRS | 1 GB/Month | 0.045 | 1 | 0.1 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-6 | Azure Retail Prices API, Tables / LRS Data Stored, southeastasia, USD per 1 GB/Month, meterId 3f2b1e1c-c886-4ec6-ad6f-dd0ef38819c9, fetched 2026-09-28 | assumption: under 0.1 GB | Dev
4 | Key Vault | Key Vault | Standard, operations | 10K | 0.03 | 1 | 0.5 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-11 | Azure Retail Prices API, Key Vault / Operations, southeastasia, USD per 10K, meterId 0f824807-2376-435c-95c9-f992b67a07b0, fetched 2026-09-28 | assumption: ~5K secret reads a month | Dev
5 | Metric alerts | Azure Monitor | Alerts Metric Monitored, beyond first 10 free | 1/Month | 0.1 | 5 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-17 | Azure Retail Prices API, Azure Monitor / Alerts Metric Monitored, southeastasia, USD per 1/Month, meterId 6860c782-bbcc-41ed-a218-fb308dd0942e, fetched 2026-09-28 | assumption: ~10 time series per env (poison_message x 8 queues, stuck_invoices, di_pages_used_pct); first 10 per subscription free, half billed here | Dev
6 | Log Analytics + App Insights | Log Analytics | Analytics Logs ingestion, within 5 GB free | 1 GB | 0 | 1 | 2.4 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-17 | Azure Retail Prices API, Log Analytics / Analytics Logs Data Ingestion, southeastasia, USD per 1 GB, meterId 7a4feecb-f730-49f8-a801-efe03d15b862, fetched 2026-09-28 | 0.08 GB/day cap = 2.4 GB/month; both envs 4.8 GB, inside the 5 GB free tier (AD-17) | Dev
Dev
Dev
Dev
Total

## Prod
Prod environment
Azure retail list prices (pay-as-you-go) in southeastasia, USD, fetched 2026-09-28. Daily cost is the monthly cost spread over the year (x 12 / 365). Blue cells are inputs.
# | Component | Azure service | SKU / tier | Unit | Unit price (USD) | Quantity | Usage per month | Monthly cost (USD) | Daily cost (USD) | Annual cost (USD) | Cited from | Price source | Note | Environment
1 | Stage queues | Storage | Queues v2 Standard LRS, Class 1 operations | 10K | 0.004 | 1 | 30 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-2 | Azure Retail Prices API, Queues v2 / LRS Class 1 Operations, southeastasia, USD per 10K, meterId a7193db3-642b-4d6f-ad03-ed5f00153bbd, fetched 2026-09-28 | assumption: ~300K ops/month from queue-trigger polling, matching AD-2's ~$0.12/month | Prod
2 | Blobs: images, corrections (30-day) | Storage | Block Blob v2 Hot LRS | 1 GB/Month | 0.02 | 2 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-15 | Azure Retail Prices API, General Block Blob v2 / Hot LRS Data Stored, southeastasia, USD per 1 GB/Month, meterId fc203689-76e7-4fbe-86b9-968d73231c00, fetched 2026-09-28 | assumption: 2 GB held under 30-day lifecycle (DI page cap bounds volume, AD-8) | Prod
3 | Tables: links, keys, reminders | Storage | Tables Standard LRS | 1 GB/Month | 0.045 | 1 | 0.1 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-6 | Azure Retail Prices API, Tables / LRS Data Stored, southeastasia, USD per 1 GB/Month, meterId 3f2b1e1c-c886-4ec6-ad6f-dd0ef38819c9, fetched 2026-09-28 | assumption: under 0.1 GB | Prod
4 | Key Vault | Key Vault | Standard, operations | 10K | 0.03 | 1 | 0.5 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-11 | Azure Retail Prices API, Key Vault / Operations, southeastasia, USD per 10K, meterId 0f824807-2376-435c-95c9-f992b67a07b0, fetched 2026-09-28 | assumption: ~5K secret reads a month | Prod
5 | Metric alerts | Azure Monitor | Alerts Metric Monitored, beyond first 10 free | 1/Month | 0.1 | 5 | 1 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-17 | Azure Retail Prices API, Azure Monitor / Alerts Metric Monitored, southeastasia, USD per 1/Month, meterId 6860c782-bbcc-41ed-a218-fb308dd0942e, fetched 2026-09-28 | assumption: ~10 time series per env (poison_message x 8 queues, stuck_invoices, di_pages_used_pct); first 10 per subscription free, half billed here | Prod
6 | Log Analytics + App Insights | Log Analytics | Analytics Logs ingestion, within 5 GB free | 1 GB | 0 | 1 | 2.4 |  |  |  | _bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md AD-17 | Azure Retail Prices API, Log Analytics / Analytics Logs Data Ingestion, southeastasia, USD per 1 GB, meterId 7a4feecb-f730-49f8-a801-efe03d15b862, fetched 2026-09-28 | 0.08 GB/day cap = 2.4 GB/month; both envs 4.8 GB, inside the 5 GB free tier (AD-17) | Prod
Prod
Prod
Prod
Total

## Sources & Gaps
Sources, assumptions and gaps
Price basis
Azure Retail Prices API list prices (pay-as-you-go, no discounts), region southeastasia, USD, fetched 2026-09-28.
Rate card: Dj, in chat 2026-09-28: blended average day rate, updated 2026-09-28.
Horizon: 5 years of run after go-live, run costs rising 0% a year.
Gaps: not priced and not in any total
Team size and days: proposed 2 people x 32 days; Dj has not set them.
Run support mandays: proposed 12 a year; not set.
Revenue or counted savings: none given, so no payback or ROI (SPEC says it removes manual keying of thousands of invoices a month).
Contingency: 0% until Dj sets one.
Delivery start date: not given, so epics and sprints are undated.
Azure DevOps: assumed within the free tier (5 Basic users, 1 free Microsoft-hosted pipeline job); not priced.
Actual cloud spend: the solution is not deployed yet (no babaloo-sea-lng-* resource groups in subscription Babaloo on 2026-09-28), so there is nothing to compare.
Production volumes: F0 caps DI at 500 pages a month; SPEC's 'thousands a month' needs S0 (~$10 per 1,000 pages) and breaks P-2.
Functions Flex on-demand: within the free 100K GB-s and 250K executions a month (AD-1), so no line is priced; the billed rate beyond that is $0.000037 per GB-s.
Revenue: none given, so the Multi-Year sheet shows costs only.
Assumptions and owner statements (not from the BMad artifacts)
Team / Team member (blended): assumption: 2 people for 32 days (30 stories at ~1 story/day, AI-assisted, plus 2 days slack); Dj to confirm
Support / Team member (blended): assumption: 1 day a month for patching, dependency upgrades, DB start/stop and alert triage; Dj to confirm
Phase budget / planning changes (correct course): owner: Dj, 2026-09-28
Phase budget / test design: owner: Dj, 2026-09-28
Phase budget / merges, promotions & deploys: owner: Dj, 2026-09-28
Phase budget / governance (Jules): owner: Dj, 2026-09-28
Phase budget / architecture docs (Da Vinci): owner: Dj, 2026-09-28
Phase budget / token reporting: owner: Dj, 2026-09-28
Stamp: built 2026-09-28T22:52:18; sha256 of each cited file
_bmad-output/planning-artifacts/architecture/architecture-ocrinvoicing-2026-09-28/ARCHITECTURE-SPINE.md 0772124ce4c6
_bmad-output/planning-artifacts/epics.md ba1900bf6060
_bmad/memory/agent-scrooge/rate-card.json 86a802068a37